## Roadmap
ID | App | Workstream | Status | Priority | Phase | Target Window | Owner | Customer Outcome | Step-by-Step Tasks | Dependencies | Capability Keys | Usage Meters | Events | Artifacts | Acceptance Criteria | Verification | Evidence / Agent Notes | Research Basis | Competitive Angle | Risks / Controls
ELK-ORCA-PROD-000 | Orca | Research And Selection | Done | P0 | 0 - Research And Operating Model | Week 0 | Coordinator Agent | The next app is selected with market-backed reasoning. | Confirm Workspace, Social, Memory, Omni, OS, and Studio roadmap packets are complete; select elkhedr-orca as the next standalone app roadmap. | Previous roadmap packets | orca.roadmap | planning.roadmap.create | orca.roadmap_selected | roadmap.decision | Decision names Orca and explains its governed execution role. | Review research memo and row ELK-ORCA-PROD-000. | Research memo created 2026-06-15. | AI coding agents and MCP execution tools are growing quickly but need governance. | Orca becomes the governed enterprise execution runtime. | If app order changes, create a superseding decision row and preserve this audit trail.
ELK-ORCA-PROD-001 | Orca | Roadmap Source Of Truth | Done | P0 | 0 - Research And Operating Model | Week 0 | Orca Agent | Agents have a production task ledger they can update after each task. | Create CSV with stable IDs; include owner, status, evidence, verification, acceptance, capabilities, events, artifacts, research basis, and risks; create XLSX review workbook. | Research memo | orca.roadmap | planning.roadmap.update | orca.roadmap_created | roadmap.csv; roadmap.xlsx | CSV has 21-column shape and unique row IDs. | Load CSV with Python and XLSX with openpyxl. | Generated alongside Orca research packet. | CSV roadmaps are easier for agents to update than prose plans. | CSV is source of truth; workbook is review artifact. | Agents must update CSV first and regenerate workbook after CSV changes.
ELK-ORCA-PROD-002 | Orca | Agent Guide | Done | P0 | 0 - Research And Operating Model | Week 0 | Orca Agent | Future Orca agents know roadmap, boundaries, and execution rules. | Update Orca agent guide with research, CSV, XLSX paths; add production priorities and CSV update rules. | docs/agent-ops/apps/orca-agent.md | orca.agent | planning.agent.update | orca.agent_guide_updated | agent.guide | Guide links roadmap files and instructs CSV updates. | Review Orca Agent Guide. | Agent guide updated in this workflow. | Enterprise agent execution needs explicit operating discipline. | Keeps Orca independent while safe to integrate. | Do not let Studio, OS, Omni, or other apps import Orca runtime modules.
ELK-ORCA-PROD-003 | Orca | Contract Change Request | Done | P0 | 1 - Contracts And Boundaries | Week 1 | Contracts Agent | Customers can rely on contract change request as part of a governed Orca execution runtime. | Define the production contract for Contract Change Request; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Contracts README; app split plan | orca.contracts | orca.contracts.usage | contracts.change_requested | contract.change_request | Contract Change Request is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | python3 scripts/validate-app-contracts.py | Implemented src/contracts/change-request.js, src/server/routes/orca-contracts.js, scripts/validate-app-contracts.py, tests/unit/orca-contract-change-request.test.js, and fixtures. Updated manifest with orca.contract_change_* event/artifact types. All validation checks pass. | Coding agents and MCP runtimes require stable contracts and least-privilege boundaries. | Orca competes on governed execution rather than broad, opaque autonomy. | Reject invalid contracts and deny unknown actions/tools by default.
ELK-ORCA-PROD-004 | Orca | Manifest Validation | Done | P0 | 1 - Contracts And Boundaries | Week 1 | Orca Agent | Customers can rely on manifest validation as part of a governed Orca execution runtime. | Define the production contract for Manifest Validation; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Existing manifest | orca.manifest | orca.manifest.usage | orca.manifest_validated | app.manifest | Manifest Validation is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | cd elkhedr-orca && npm run manifest && node --test tests/unit/manifest-validation.test.js | Enhanced scripts/validate-manifest.js to validate arbitrary manifest paths, emit orca.manifest_validated event, write app.manifest artifact, and emit orca.manifest_validation_failed on failure. Added 4 synthetic fixtures and 7 unit tests. Operator docs at docs/notes/MANIFEST_VALIDATION_OPERATOR.md. | Coding agents and MCP runtimes require stable contracts and least-privilege boundaries. | Orca competes on governed execution rather than broad, opaque autonomy. | Reject invalid contracts and deny unknown actions/tools by default.
ELK-ORCA-PROD-005 | Orca | OpenAPI Service Contract | Proposed | P0 | 1 - Contracts And Boundaries | Week 1 | Contracts Agent | Customers can rely on openapi service contract as part of a governed Orca execution runtime. | Define the production contract for OpenAPI Service Contract; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Contract change request | orca.api | orca.api.usage | orca.openapi_updated | openapi.orca | OpenAPI Service Contract is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | python3 scripts/validate-app-contracts.py | Pending implementation. | Coding agents and MCP runtimes require stable contracts and least-privilege boundaries. | Orca competes on governed execution rather than broad, opaque autonomy. | Reject invalid contracts and deny unknown actions/tools by default.
ELK-ORCA-PROD-006 | Orca | MCP Schema Contract | Proposed | P0 | 1 - Contracts And Boundaries | Week 1 | Contracts Agent | Customers can rely on mcp schema contract as part of a governed Orca execution runtime. | Define the production contract for MCP Schema Contract; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | MCP server; OpenAPI | orca.mcp | orca.mcp.usage | orca.mcp_schema_updated | mcp.schema | MCP Schema Contract is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | MCP schema validation tests pass. | Pending implementation. | Coding agents and MCP runtimes require stable contracts and least-privilege boundaries. | Orca competes on governed execution rather than broad, opaque autonomy. | Reject invalid contracts and deny unknown actions/tools by default.
ELK-ORCA-PROD-007 | Orca | Action Approval Contract | Proposed | P0 | 1 - Contracts And Boundaries | Week 1 | Contracts Agent | Customers can rely on action approval contract as part of a governed Orca execution runtime. | Define the production contract for Action Approval Contract; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Existing action store | orca.actions; orca.approvals | orca.actions.usage; orca.approvals.usage | orca.action_requested; orca.action_approved; orca.action_rejected | orca.action | Action Approval Contract is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | node --test tests/unit/orca-action-contract.test.js | Pending implementation. | Coding agents and MCP runtimes require stable contracts and least-privilege boundaries. | Orca competes on governed execution rather than broad, opaque autonomy. | Reject invalid contracts and deny unknown actions/tools by default.
ELK-ORCA-PROD-008 | Orca | Event Contracts | Proposed | P0 | 1 - Contracts And Boundaries | Week 1 | Contracts Agent | Customers can rely on event contracts as part of a governed Orca execution runtime. | Define the production contract for Event Contracts; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Action contract; OS event envelope | orca.events | orca.events.usage | orca.run_started; orca.action_requested; orca.run_completed | orca.event.ref | Event Contracts is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Event fixture validation passes. | Pending implementation. | Coding agents and MCP runtimes require stable contracts and least-privilege boundaries. | Orca competes on governed execution rather than broad, opaque autonomy. | Reject invalid contracts and deny unknown actions/tools by default.
ELK-ORCA-PROD-009 | Orca | Artifact Contracts | Proposed | P0 | 1 - Contracts And Boundaries | Week 1 | Contracts Agent | Customers can rely on artifact contracts as part of a governed Orca execution runtime. | Define the production contract for Artifact Contracts; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Event contracts | orca.artifacts | orca.artifacts.usage | orca.artifact_created | orca.run; orca.report; orca.patch | Artifact Contracts is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Artifact fixture validation passes. | Pending implementation. | Coding agents and MCP runtimes require stable contracts and least-privilege boundaries. | Orca competes on governed execution rather than broad, opaque autonomy. | Reject invalid contracts and deny unknown actions/tools by default.
ELK-ORCA-PROD-010 | Orca | Capability Registry | Proposed | P0 | 1 - Contracts And Boundaries | Week 1 | Orca Agent | Customers can rely on capability registry as part of a governed Orca execution runtime. | Define the production contract for Capability Registry; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Manifest; entitlement gateway | orca.* | orca.*.usage | orca.capability_registered | capability.registry | Capability Registry is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | npm run production:check | Pending implementation. | Coding agents and MCP runtimes require stable contracts and least-privilege boundaries. | Orca competes on governed execution rather than broad, opaque autonomy. | Reject invalid contracts and deny unknown actions/tools by default.
ELK-ORCA-PROD-011 | Orca | Usage Meters | Proposed | P0 | 1 - Contracts And Boundaries | Week 1 | Orca Agent | Customers can rely on usage meters as part of a governed Orca execution runtime. | Define the production contract for Usage Meters; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Capability Registry | orca.usage | orca.usage.usage | orca.usage_recorded | usage.meter | Usage Meters is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Usage meter tests pass. | Pending implementation. | Coding agents and MCP runtimes require stable contracts and least-privilege boundaries. | Orca competes on governed execution rather than broad, opaque autonomy. | Reject invalid contracts and deny unknown actions/tools by default.
ELK-ORCA-PROD-012 | Orca | Agent Registry Schema | Proposed | P0 | 1 - Contracts And Boundaries | Week 1 | Contracts Agent | Customers can rely on agent registry schema as part of a governed Orca execution runtime. | Define the production contract for Agent Registry Schema; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Existing agents.json | orca.agents | orca.agents.usage | orca.agent_schema_updated | agent.schema | Agent Registry Schema is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Agent schema fixture validation passes. | Pending implementation. | Coding agents and MCP runtimes require stable contracts and least-privilege boundaries. | Orca competes on governed execution rather than broad, opaque autonomy. | Reject invalid contracts and deny unknown actions/tools by default.
ELK-ORCA-PROD-013 | Orca | Session Run Schema | Proposed | P0 | 1 - Contracts And Boundaries | Week 1 | Contracts Agent | Customers can rely on session run schema as part of a governed Orca execution runtime. | Define the production contract for Session Run Schema; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | OpenAPI service contract | orca.sessions; orca.runs | orca.sessions.usage; orca.runs.usage | orca.run_schema_updated | run.schema | Session Run Schema is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Run schema tests pass. | Pending implementation. | Coding agents and MCP runtimes require stable contracts and least-privilege boundaries. | Orca competes on governed execution rather than broad, opaque autonomy. | Reject invalid contracts and deny unknown actions/tools by default.
ELK-ORCA-PROD-014 | Orca | Sandbox Profile Schema | Proposed | P0 | 1 - Contracts And Boundaries | Week 1 | Security Agent | Customers can rely on sandbox profile schema as part of a governed Orca execution runtime. | Define the production contract for Sandbox Profile Schema; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Action contract | orca.sandbox | orca.sandbox.usage | orca.sandbox_profile_updated | sandbox.profile | Sandbox Profile Schema is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Sandbox schema tests pass. | Pending implementation. | Coding agents and MCP runtimes require stable contracts and least-privilege boundaries. | Orca competes on governed execution rather than broad, opaque autonomy. | Reject invalid contracts and deny unknown actions/tools by default.
ELK-ORCA-PROD-015 | Orca | Tool Policy Schema | Proposed | P0 | 1 - Contracts And Boundaries | Week 1 | Security Agent | Customers can rely on tool policy schema as part of a governed Orca execution runtime. | Define the production contract for Tool Policy Schema; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | MCP schema; sandbox profile | orca.tools | orca.tools.usage | orca.tool_policy_updated | tool.policy | Tool Policy Schema is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Tool policy fixture tests pass. | Pending implementation. | Coding agents and MCP runtimes require stable contracts and least-privilege boundaries. | Orca competes on governed execution rather than broad, opaque autonomy. | Reject invalid contracts and deny unknown actions/tools by default.
ELK-ORCA-PROD-016 | Orca | Boundary Policy | Proposed | P0 | 1 - Contracts And Boundaries | Week 1 | Coordinator Agent | Customers can rely on boundary policy as part of a governed Orca execution runtime. | Define the production contract for Boundary Policy; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Standalone app separation guide | orca.boundaries | orca.boundaries.usage | orca.boundary_policy_updated | boundary.policy | Boundary Policy is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | python3 scripts/check-app-boundaries.py | Pending implementation. | Coding agents and MCP runtimes require stable contracts and least-privilege boundaries. | Orca competes on governed execution rather than broad, opaque autonomy. | Reject invalid contracts and deny unknown actions/tools by default.
ELK-ORCA-PROD-017 | Orca | Baseline Runtime Audit | Proposed | P0 | 2 - CLI MCP Service Foundation | Week 1-2 | Orca Agent | Customers can rely on baseline runtime audit as part of a governed Orca execution runtime. | Define the production contract for Baseline Runtime Audit; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Existing Orca runtime | orca.health | orca.health.usage | orca.baseline_audited | baseline.report | Baseline Runtime Audit is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | cd elkhedr-orca && npm run manifest && npm test | Pending implementation. | Terminal agents must be reliable, observable, and easy to install before autonomy. | A hardened CLI/MCP/service foundation makes Orca usable without Studio. | Default checks must remain resource efficient and never launch long autonomous loops.
ELK-ORCA-PROD-018 | Orca | CLI Command Hardening | Proposed | P0 | 2 - CLI MCP Service Foundation | Week 1-2 | Orca Agent | Customers can rely on cli command hardening as part of a governed Orca execution runtime. | Define the production contract for CLI Command Hardening; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | src/index.js; cli args | orca.cli | orca.cli.usage | orca.cli_hardened | cli.report | CLI Command Hardening is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | node --check src/index.js | Pending implementation. | Terminal agents must be reliable, observable, and easy to install before autonomy. | A hardened CLI/MCP/service foundation makes Orca usable without Studio. | Default checks must remain resource efficient and never launch long autonomous loops.
ELK-ORCA-PROD-019 | Orca | TUI Hardening | Proposed | P1 | 2 - CLI MCP Service Foundation | Week 1-2 | Orca Agent | Customers can rely on tui hardening as part of a governed Orca execution runtime. | Define the production contract for TUI Hardening; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | src/tui.js | orca.tui | orca.tui.usage | orca.tui_hardened | tui.report | TUI Hardening is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | node --check src/tui.js where present | Pending implementation. | Terminal agents must be reliable, observable, and easy to install before autonomy. | A hardened CLI/MCP/service foundation makes Orca usable without Studio. | Default checks must remain resource efficient and never launch long autonomous loops.
ELK-ORCA-PROD-020 | Orca | Service Mode API Server | Proposed | P0 | 2 - CLI MCP Service Foundation | Week 1-2 | Orca Agent | Customers can rely on service mode api server as part of a governed Orca execution runtime. | Define the production contract for Service Mode API Server; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | src/server/index.js; service routes | orca.service | orca.service.usage | orca.service_ready | service.report | Service Mode API Server is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | node --check src/server/index.js where present | Pending implementation. | Terminal agents must be reliable, observable, and easy to install before autonomy. | A hardened CLI/MCP/service foundation makes Orca usable without Studio. | Default checks must remain resource efficient and never launch long autonomous loops.
ELK-ORCA-PROD-021 | Orca | Service Status Endpoint | Proposed | P0 | 2 - CLI MCP Service Foundation | Week 1-2 | Orca Agent | Customers can rely on service status endpoint as part of a governed Orca execution runtime. | Define the production contract for Service Status Endpoint; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Service routes | orca.status | orca.status.usage | orca.status_checked | status.response | Service Status Endpoint is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Parent compose full-smoke when Orca is running. | Pending implementation. | Terminal agents must be reliable, observable, and easy to install before autonomy. | A hardened CLI/MCP/service foundation makes Orca usable without Studio. | Default checks must remain resource efficient and never launch long autonomous loops.
ELK-ORCA-PROD-022 | Orca | Configuration Surface | Proposed | P0 | 2 - CLI MCP Service Foundation | Week 1-2 | Orca Agent | Customers can rely on configuration surface as part of a governed Orca execution runtime. | Define the production contract for Configuration Surface; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Config modules | orca.settings | orca.settings.usage | orca.config_updated | config.schema | Configuration Surface is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Config tests pass. | Pending implementation. | Terminal agents must be reliable, observable, and easy to install before autonomy. | A hardened CLI/MCP/service foundation makes Orca usable without Studio. | Default checks must remain resource efficient and never launch long autonomous loops.
ELK-ORCA-PROD-023 | Orca | Data Directory Bootstrap | Proposed | P0 | 2 - CLI MCP Service Foundation | Week 1-2 | Orca Agent | Customers can rely on data directory bootstrap as part of a governed Orca execution runtime. | Define the production contract for Data Directory Bootstrap; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Configuration surface | orca.storage | orca.storage.usage | orca.store_initialized | storage.metadata | Data Directory Bootstrap is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Run with temporary data dir and create a sample session. | Pending implementation. | Terminal agents must be reliable, observable, and easy to install before autonomy. | A hardened CLI/MCP/service foundation makes Orca usable without Studio. | Default checks must remain resource efficient and never launch long autonomous loops.
ELK-ORCA-PROD-024 | Orca | Database Migrations | Proposed | P0 | 2 - CLI MCP Service Foundation | Week 1-2 | Orca Agent | Customers can rely on database migrations as part of a governed Orca execution runtime. | Define the production contract for Database Migrations; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | src/db migrations | orca.migrations | orca.migrations.usage | orca.store_migrated | migration.log | Database Migrations is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | npm run db:migrate:status and migration tests pass. | Pending implementation. | Terminal agents must be reliable, observable, and easy to install before autonomy. | A hardened CLI/MCP/service foundation makes Orca usable without Studio. | Default checks must remain resource efficient and never launch long autonomous loops.
ELK-ORCA-PROD-025 | Orca | Backup Restore | Proposed | P0 | 2 - CLI MCP Service Foundation | Week 1-2 | Orca Agent | Customers can rely on backup restore as part of a governed Orca execution runtime. | Define the production contract for Backup Restore; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Backup scripts | orca.backup | orca.backup.usage | orca.backup_created; orca.restore_completed | backup.pack | Backup Restore is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Backup/restore tests pass. | Pending implementation. | Terminal agents must be reliable, observable, and easy to install before autonomy. | A hardened CLI/MCP/service foundation makes Orca usable without Studio. | Default checks must remain resource efficient and never launch long autonomous loops.
ELK-ORCA-PROD-026 | Orca | Install Script Hardening | Proposed | P0 | 2 - CLI MCP Service Foundation | Week 1-2 | Security Agent | Customers can rely on install script hardening as part of a governed Orca execution runtime. | Define the production contract for Install Script Hardening; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | install.sh | orca.install | orca.install.usage | orca.install_checked | install.report | Install Script Hardening is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | bash -n install.sh | Pending implementation. | Terminal agents must be reliable, observable, and easy to install before autonomy. | A hardened CLI/MCP/service foundation makes Orca usable without Studio. | Default checks must remain resource efficient and never launch long autonomous loops.
ELK-ORCA-PROD-027 | Orca | Health Readiness Checks | Proposed | P0 | 2 - CLI MCP Service Foundation | Week 1-2 | Orca Agent | Customers can rely on health readiness checks as part of a governed Orca execution runtime. | Define the production contract for Health Readiness Checks; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Service status; config | orca.health | orca.health.usage | orca.health_checked | health.report | Health Readiness Checks is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | npm run health and service health tests pass. | Pending implementation. | Terminal agents must be reliable, observable, and easy to install before autonomy. | A hardened CLI/MCP/service foundation makes Orca usable without Studio. | Default checks must remain resource efficient and never launch long autonomous loops.
ELK-ORCA-PROD-028 | Orca | Logging Redaction | Proposed | P0 | 2 - CLI MCP Service Foundation | Week 1-2 | Security Agent | Customers can rely on logging redaction as part of a governed Orca execution runtime. | Define the production contract for Logging Redaction; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Logger utilities | orca.logs | orca.logs.usage | orca.log_redacted | support.log | Logging Redaction is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Log redaction tests and sample inspection pass. | Pending implementation. | Terminal agents must be reliable, observable, and easy to install before autonomy. | A hardened CLI/MCP/service foundation makes Orca usable without Studio. | Default checks must remain resource efficient and never launch long autonomous loops.
ELK-ORCA-PROD-029 | Orca | Resource Modes | Proposed | P1 | 2 - CLI MCP Service Foundation | Week 1-2 | Orca Agent | Customers can rely on resource modes as part of a governed Orca execution runtime. | Define the production contract for Resource Modes; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | README resource budgets | orca.resource_mode | orca.resource_mode.usage | orca.resource_mode_updated | resource.profile | Resource Modes is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Docs and scripts reflect resource modes. | Pending implementation. | Terminal agents must be reliable, observable, and easy to install before autonomy. | A hardened CLI/MCP/service foundation makes Orca usable without Studio. | Default checks must remain resource efficient and never launch long autonomous loops.
ELK-ORCA-PROD-030 | Orca | Session Model | Proposed | P0 | 3 - Sessions Runs Agents | Week 3-4 | Orca Agent | Customers can rely on session model as part of a governed Orca execution runtime. | Define the production contract for Session Model; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Session schema | orca.sessions | orca.sessions.usage | orca.session_created | orca.session | Session Model is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Session tests pass. | Pending implementation. | Codex, Copilot, and Devin-style agents depend on durable background sessions and reviewable plans. | Orca can use multi-agent execution only where state, budget, and evidence are measurable. | No production run state should live only in memory or bypass checkpoints.
ELK-ORCA-PROD-031 | Orca | Run State Machine | Proposed | P0 | 3 - Sessions Runs Agents | Week 3-4 | Orca Agent | Customers can rely on run state machine as part of a governed Orca execution runtime. | Define the production contract for Run State Machine; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Run schema | orca.runs | orca.runs.usage | orca.run_state_changed | orca.run | Run State Machine is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Run state tests pass. | Pending implementation. | Codex, Copilot, and Devin-style agents depend on durable background sessions and reviewable plans. | Orca can use multi-agent execution only where state, budget, and evidence are measurable. | No production run state should live only in memory or bypass checkpoints.
ELK-ORCA-PROD-032 | Orca | Plan Generation | Proposed | P0 | 3 - Sessions Runs Agents | Week 3-4 | Orca Agent | Customers can rely on plan generation as part of a governed Orca execution runtime. | Define the production contract for Plan Generation; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Run state machine; model adapter | orca.planning | orca.planning.usage | orca.plan_created | orca.plan | Plan Generation is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Plan tests with fake model pass. | Pending implementation. | Codex, Copilot, and Devin-style agents depend on durable background sessions and reviewable plans. | Orca can use multi-agent execution only where state, budget, and evidence are measurable. | No production run state should live only in memory or bypass checkpoints.
ELK-ORCA-PROD-033 | Orca | Task Decomposition | Proposed | P1 | 3 - Sessions Runs Agents | Week 3-4 | Orca Agent | Customers can rely on task decomposition as part of a governed Orca execution runtime. | Define the production contract for Task Decomposition; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Plan generation | orca.decomposition | orca.decomposition.usage | orca.task_decomposed | task.plan | Task Decomposition is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Decomposition tests pass. | Pending implementation. | Codex, Copilot, and Devin-style agents depend on durable background sessions and reviewable plans. | Orca can use multi-agent execution only where state, budget, and evidence are measurable. | No production run state should live only in memory or bypass checkpoints.
ELK-ORCA-PROD-034 | Orca | Checkpoints | Proposed | P0 | 3 - Sessions Runs Agents | Week 3-4 | Orca Agent | Customers can rely on checkpoints as part of a governed Orca execution runtime. | Define the production contract for Checkpoints; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Run state machine; approvals | orca.checkpoints | orca.checkpoints.usage | orca.checkpoint_created | checkpoint.record | Checkpoints is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Checkpoint tests pass. | Pending implementation. | Codex, Copilot, and Devin-style agents depend on durable background sessions and reviewable plans. | Orca can use multi-agent execution only where state, budget, and evidence are measurable. | No production run state should live only in memory or bypass checkpoints.
ELK-ORCA-PROD-035 | Orca | Agent Registry Runtime | Proposed | P0 | 3 - Sessions Runs Agents | Week 3-4 | Orca Agent | Customers can rely on agent registry runtime as part of a governed Orca execution runtime. | Define the production contract for Agent Registry Runtime; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Agent schema | orca.agents | orca.agents.usage | orca.agent_registry_loaded | agent.registry | Agent Registry Runtime is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Agent registry tests pass. | Pending implementation. | Codex, Copilot, and Devin-style agents depend on durable background sessions and reviewable plans. | Orca can use multi-agent execution only where state, budget, and evidence are measurable. | No production run state should live only in memory or bypass checkpoints.
ELK-ORCA-PROD-036 | Orca | Model Routing Policy | Proposed | P0 | 3 - Sessions Runs Agents | Week 3-4 | Orca Agent | Customers can rely on model routing policy as part of a governed Orca execution runtime. | Define the production contract for Model Routing Policy; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Provider config; usage meters | orca.models | orca.models.usage | orca.model_routed | model.route | Model Routing Policy is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Model routing tests pass. | Pending implementation. | Codex, Copilot, and Devin-style agents depend on durable background sessions and reviewable plans. | Orca can use multi-agent execution only where state, budget, and evidence are measurable. | No production run state should live only in memory or bypass checkpoints.
ELK-ORCA-PROD-037 | Orca | Fallback And Circuit Breakers | Proposed | P0 | 3 - Sessions Runs Agents | Week 3-4 | Orca Agent | Customers can rely on fallback and circuit breakers as part of a governed Orca execution runtime. | Define the production contract for Fallback And Circuit Breakers; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Existing circuit breaker utils | orca.resilience | orca.resilience.usage | orca.circuit_opened; orca.retry_scheduled | resilience.report | Fallback And Circuit Breakers is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Resilience tests pass. | Pending implementation. | Codex, Copilot, and Devin-style agents depend on durable background sessions and reviewable plans. | Orca can use multi-agent execution only where state, budget, and evidence are measurable. | No production run state should live only in memory or bypass checkpoints.
ELK-ORCA-PROD-038 | Orca | Team Orchestration | Proposed | P1 | 3 - Sessions Runs Agents | Week 3-4 | Orca Agent | Customers can rely on team orchestration as part of a governed Orca execution runtime. | Define the production contract for Team Orchestration; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Agent registry | orca.teams | orca.teams.usage | orca.team_assigned | team.plan | Team Orchestration is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Team orchestration tests pass. | Pending implementation. | Codex, Copilot, and Devin-style agents depend on durable background sessions and reviewable plans. | Orca can use multi-agent execution only where state, budget, and evidence are measurable. | No production run state should live only in memory or bypass checkpoints.
ELK-ORCA-PROD-039 | Orca | Conflict Resolution | Proposed | P1 | 3 - Sessions Runs Agents | Week 3-4 | Orca Agent | Customers can rely on conflict resolution as part of a governed Orca execution runtime. | Define the production contract for Conflict Resolution; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Swarm strategies | orca.conflicts | orca.conflicts.usage | orca.conflict_resolved | conflict.report | Conflict Resolution is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Conflict tests pass. | Pending implementation. | Codex, Copilot, and Devin-style agents depend on durable background sessions and reviewable plans. | Orca can use multi-agent execution only where state, budget, and evidence are measurable. | No production run state should live only in memory or bypass checkpoints.
ELK-ORCA-PROD-040 | Orca | Cost Budgets | Proposed | P0 | 3 - Sessions Runs Agents | Week 3-4 | Orca Agent | Customers can rely on cost budgets as part of a governed Orca execution runtime. | Define the production contract for Cost Budgets; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Usage meters; model policy | orca.budgets | orca.budgets.usage | orca.budget_exceeded | budget.record | Cost Budgets is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Budget tests pass. | Pending implementation. | Codex, Copilot, and Devin-style agents depend on durable background sessions and reviewable plans. | Orca can use multi-agent execution only where state, budget, and evidence are measurable. | No production run state should live only in memory or bypass checkpoints.
ELK-ORCA-PROD-041 | Orca | Cancel Resume Retry | Proposed | P0 | 3 - Sessions Runs Agents | Week 3-4 | Orca Agent | Customers can rely on cancel resume retry as part of a governed Orca execution runtime. | Define the production contract for Cancel Resume Retry; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Run state machine | orca.runs | orca.runs.usage | orca.run_canceled; orca.run_resumed; orca.run_retried | run.control | Cancel Resume Retry is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Control tests pass. | Pending implementation. | Codex, Copilot, and Devin-style agents depend on durable background sessions and reviewable plans. | Orca can use multi-agent execution only where state, budget, and evidence are measurable. | No production run state should live only in memory or bypass checkpoints.
ELK-ORCA-PROD-042 | Orca | Run History Search | Proposed | P1 | 3 - Sessions Runs Agents | Week 3-4 | Orca Agent | Customers can rely on run history search as part of a governed Orca execution runtime. | Define the production contract for Run History Search; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Session/run model | orca.search | orca.search.usage | orca.run_search_performed | search.result | Run History Search is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Search tests pass. | Pending implementation. | Codex, Copilot, and Devin-style agents depend on durable background sessions and reviewable plans. | Orca can use multi-agent execution only where state, budget, and evidence are measurable. | No production run state should live only in memory or bypass checkpoints.
ELK-ORCA-PROD-043 | Orca | Action Taxonomy | Proposed | P0 | 4 - Action Approvals And Sandboxing | Week 5-6 | Security Agent | Customers can rely on action taxonomy as part of a governed Orca execution runtime. | Define the production contract for Action Taxonomy; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Action approval contract | orca.actions | orca.actions.usage | orca.action_taxonomy_updated | action.taxonomy | Action Taxonomy is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Taxonomy tests pass. | Pending implementation. | Claude Code permissions/sandboxing and MCP security guidance show autonomy must be permissioned. | Governed action execution is Orca’s primary trust differentiator. | Approval, sandbox, secret, and policy test failures block release.
ELK-ORCA-PROD-044 | Orca | Approval Queue | Proposed | P0 | 4 - Action Approvals And Sandboxing | Week 5-6 | Orca Agent | Customers can rely on approval queue as part of a governed Orca execution runtime. | Define the production contract for Approval Queue; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Action contract | orca.approvals | orca.approvals.usage | orca.action_requested; orca.action_approved; orca.action_rejected | approval.record | Approval Queue is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Action contract tests pass. | Pending implementation. | Claude Code permissions/sandboxing and MCP security guidance show autonomy must be permissioned. | Governed action execution is Orca’s primary trust differentiator. | Approval, sandbox, secret, and policy test failures block release.
ELK-ORCA-PROD-045 | Orca | High Risk Approval Rules | Proposed | P0 | 4 - Action Approvals And Sandboxing | Week 5-6 | Security Agent | Customers can rely on high risk approval rules as part of a governed Orca execution runtime. | Define the production contract for High Risk Approval Rules; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Approval Queue; Action Taxonomy | orca.approvals; orca.policy | orca.approvals.usage; orca.policy.usage | orca.high_risk_action_blocked | high_risk.policy | High Risk Approval Rules is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | High-risk tests pass. | Pending implementation. | Claude Code permissions/sandboxing and MCP security guidance show autonomy must be permissioned. | Governed action execution is Orca’s primary trust differentiator. | Approval, sandbox, secret, and policy test failures block release.
ELK-ORCA-PROD-046 | Orca | Deny Ask Allow Policy | Proposed | P0 | 4 - Action Approvals And Sandboxing | Week 5-6 | Security Agent | Customers can rely on deny ask allow policy as part of a governed Orca execution runtime. | Define the production contract for Deny Ask Allow Policy; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Action taxonomy | orca.permissions | orca.permissions.usage | orca.permission_decision | permission.policy | Deny Ask Allow Policy is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Permission tests pass. | Pending implementation. | Claude Code permissions/sandboxing and MCP security guidance show autonomy must be permissioned. | Governed action execution is Orca’s primary trust differentiator. | Approval, sandbox, secret, and policy test failures block release.
ELK-ORCA-PROD-047 | Orca | Sandbox Profiles Runtime | Proposed | P0 | 4 - Action Approvals And Sandboxing | Week 5-6 | Security Agent | Customers can rely on sandbox profiles runtime as part of a governed Orca execution runtime. | Define the production contract for Sandbox Profiles Runtime; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Sandbox profile schema | orca.sandbox | orca.sandbox.usage | orca.sandbox_started; orca.sandbox_blocked | sandbox.session | Sandbox Profiles Runtime is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Sandbox runtime tests pass. | Pending implementation. | Claude Code permissions/sandboxing and MCP security guidance show autonomy must be permissioned. | Governed action execution is Orca’s primary trust differentiator. | Approval, sandbox, secret, and policy test failures block release.
ELK-ORCA-PROD-048 | Orca | Read Only Sandbox | Proposed | P0 | 4 - Action Approvals And Sandboxing | Week 5-6 | Security Agent | Customers can rely on read only sandbox as part of a governed Orca execution runtime. | Define the production contract for Read Only Sandbox; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Sandbox profiles | orca.sandbox.read_only | orca.sandbox.read_only.usage | orca.sandbox_read_only_started | sandbox.profile | Read Only Sandbox is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Read-only tests pass. | Pending implementation. | Claude Code permissions/sandboxing and MCP security guidance show autonomy must be permissioned. | Governed action execution is Orca’s primary trust differentiator. | Approval, sandbox, secret, and policy test failures block release.
ELK-ORCA-PROD-049 | Orca | Patch Only Sandbox | Proposed | P0 | 4 - Action Approvals And Sandboxing | Week 5-6 | Security Agent | Customers can rely on patch only sandbox as part of a governed Orca execution runtime. | Define the production contract for Patch Only Sandbox; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Sandbox profiles; patch artifacts | orca.sandbox.patch | orca.sandbox.patch.usage | orca.patch_created | orca.patch | Patch Only Sandbox is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Patch sandbox tests pass. | Pending implementation. | Claude Code permissions/sandboxing and MCP security guidance show autonomy must be permissioned. | Governed action execution is Orca’s primary trust differentiator. | Approval, sandbox, secret, and policy test failures block release.
ELK-ORCA-PROD-050 | Orca | Shell Command Policy | Proposed | P0 | 4 - Action Approvals And Sandboxing | Week 5-6 | Security Agent | Customers can rely on shell command policy as part of a governed Orca execution runtime. | Define the production contract for Shell Command Policy; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Action taxonomy; sandbox | orca.shell | orca.shell.usage | orca.shell_command_requested; orca.shell_command_completed | shell.record | Shell Command Policy is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Shell policy tests pass. | Pending implementation. | Claude Code permissions/sandboxing and MCP security guidance show autonomy must be permissioned. | Governed action execution is Orca’s primary trust differentiator. | Approval, sandbox, secret, and policy test failures block release.
ELK-ORCA-PROD-051 | Orca | File Write Delete Policy | Proposed | P0 | 4 - Action Approvals And Sandboxing | Week 5-6 | Security Agent | Customers can rely on file write delete policy as part of a governed Orca execution runtime. | Define the production contract for File Write Delete Policy; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Patch sandbox | orca.files | orca.files.usage | orca.file_write_requested; orca.file_delete_blocked | file.action_record | File Write Delete Policy is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | File policy tests pass. | Pending implementation. | Claude Code permissions/sandboxing and MCP security guidance show autonomy must be permissioned. | Governed action execution is Orca’s primary trust differentiator. | Approval, sandbox, secret, and policy test failures block release.
ELK-ORCA-PROD-052 | Orca | Browser Desktop Policy | Proposed | P0 | 4 - Action Approvals And Sandboxing | Week 5-6 | Security Agent | Customers can rely on browser desktop policy as part of a governed Orca execution runtime. | Define the production contract for Browser Desktop Policy; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Action taxonomy | orca.browser; orca.desktop | orca.browser.usage; orca.desktop.usage | orca.browser_action_requested; orca.desktop_action_blocked | browser.action_record | Browser Desktop Policy is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Browser/desktop policy tests pass. | Pending implementation. | Claude Code permissions/sandboxing and MCP security guidance show autonomy must be permissioned. | Governed action execution is Orca’s primary trust differentiator. | Approval, sandbox, secret, and policy test failures block release.
ELK-ORCA-PROD-053 | Orca | Network Policy | Proposed | P0 | 4 - Action Approvals And Sandboxing | Week 5-6 | Security Agent | Customers can rely on network policy as part of a governed Orca execution runtime. | Define the production contract for Network Policy; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Sandbox runtime | orca.network | orca.network.usage | orca.network_request_blocked | network.policy | Network Policy is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Network policy tests pass. | Pending implementation. | Claude Code permissions/sandboxing and MCP security guidance show autonomy must be permissioned. | Governed action execution is Orca’s primary trust differentiator. | Approval, sandbox, secret, and policy test failures block release.
ELK-ORCA-PROD-054 | Orca | Secrets Redaction Guard | Proposed | P0 | 4 - Action Approvals And Sandboxing | Week 5-6 | Security Agent | Customers can rely on secrets redaction guard as part of a governed Orca execution runtime. | Define the production contract for Secrets Redaction Guard; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Logging; provider policy | orca.secrets | orca.secrets.usage | orca.secret_detected | secret.scan_report | Secrets Redaction Guard is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Secret guard tests pass. | Pending implementation. | Claude Code permissions/sandboxing and MCP security guidance show autonomy must be permissioned. | Governed action execution is Orca’s primary trust differentiator. | Approval, sandbox, secret, and policy test failures block release.
ELK-ORCA-PROD-055 | Orca | Idempotency Keys | Proposed | P0 | 4 - Action Approvals And Sandboxing | Week 5-6 | Orca Agent | Customers can rely on idempotency keys as part of a governed Orca execution runtime. | Define the production contract for Idempotency Keys; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Run controls; integrations | orca.idempotency | orca.idempotency.usage | orca.idempotency_reused | idempotency.record | Idempotency Keys is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Idempotency tests pass. | Pending implementation. | Claude Code permissions/sandboxing and MCP security guidance show autonomy must be permissioned. | Governed action execution is Orca’s primary trust differentiator. | Approval, sandbox, secret, and policy test failures block release.
ELK-ORCA-PROD-056 | Orca | Rollback Evidence | Proposed | P0 | 4 - Action Approvals And Sandboxing | Week 5-6 | Orca Agent | Customers can rely on rollback evidence as part of a governed Orca execution runtime. | Define the production contract for Rollback Evidence; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Patch artifacts; file policy | orca.rollback | orca.rollback.usage | orca.rollback_plan_created | rollback.plan | Rollback Evidence is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Rollback tests pass. | Pending implementation. | Claude Code permissions/sandboxing and MCP security guidance show autonomy must be permissioned. | Governed action execution is Orca’s primary trust differentiator. | Approval, sandbox, secret, and policy test failures block release.
ELK-ORCA-PROD-057 | Orca | Policy Test Suite | Proposed | P0 | 4 - Action Approvals And Sandboxing | Week 5-6 | QA Agent | Customers can rely on policy test suite as part of a governed Orca execution runtime. | Define the production contract for Policy Test Suite; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | All action policies | orca.policy_tests | orca.policy_tests.usage | orca.policy_tests_completed | policy.test_report | Policy Test Suite is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Policy suite passes. | Pending implementation. | Claude Code permissions/sandboxing and MCP security guidance show autonomy must be permissioned. | Governed action execution is Orca’s primary trust differentiator. | Approval, sandbox, secret, and policy test failures block release.
ELK-ORCA-PROD-058 | Orca | MCP Server Hardening | Proposed | P0 | 5 - MCP Tools Integrations | Week 7-8 | Orca Agent | Customers can rely on mcp server hardening as part of a governed Orca execution runtime. | Define the production contract for MCP Server Hardening; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | MCP schema contract | orca.mcp | orca.mcp.usage | orca.mcp_server_hardened | mcp.server_report | MCP Server Hardening is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | node --check src/mcp-server.js and MCP tests pass. | Pending implementation. | Gemini CLI, MCP, and enterprise coding agents are expanding through tool ecosystems. | Orca can be a safe CLI/MCP runtime for approved tools and integrations. | Fake adapters are required; no real credentials in default tests.
ELK-ORCA-PROD-059 | Orca | MCP Authorization | Proposed | P0 | 5 - MCP Tools Integrations | Week 7-8 | Security Agent | Customers can rely on mcp authorization as part of a governed Orca execution runtime. | Define the production contract for MCP Authorization; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | MCP authorization spec | orca.mcp_auth | orca.mcp_auth.usage | orca.mcp_auth_updated | mcp.auth_policy | MCP Authorization is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | MCP auth tests pass or documented local-only limitation exists. | Pending implementation. | Gemini CLI, MCP, and enterprise coding agents are expanding through tool ecosystems. | Orca can be a safe CLI/MCP runtime for approved tools and integrations. | Fake adapters are required; no real credentials in default tests.
ELK-ORCA-PROD-060 | Orca | Tool Registry | Proposed | P0 | 5 - MCP Tools Integrations | Week 7-8 | Orca Agent | Customers can rely on tool registry as part of a governed Orca execution runtime. | Define the production contract for Tool Registry; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Tool policy schema | orca.tools | orca.tools.usage | orca.tool_registered | tool.registry | Tool Registry is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Tool registry tests pass. | Pending implementation. | Gemini CLI, MCP, and enterprise coding agents are expanding through tool ecosystems. | Orca can be a safe CLI/MCP runtime for approved tools and integrations. | Fake adapters are required; no real credentials in default tests.
ELK-ORCA-PROD-061 | Orca | Tool Allowlist | Proposed | P0 | 5 - MCP Tools Integrations | Week 7-8 | Security Agent | Customers can rely on tool allowlist as part of a governed Orca execution runtime. | Define the production contract for Tool Allowlist; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Tool Registry | orca.tools; orca.policy | orca.tools.usage; orca.policy.usage | orca.tool_blocked; orca.tool_allowed | tool.policy_decision | Tool Allowlist is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Allowlist tests pass. | Pending implementation. | Gemini CLI, MCP, and enterprise coding agents are expanding through tool ecosystems. | Orca can be a safe CLI/MCP runtime for approved tools and integrations. | Fake adapters are required; no real credentials in default tests.
ELK-ORCA-PROD-062 | Orca | MCP Client Connectors | Proposed | P1 | 5 - MCP Tools Integrations | Week 7-8 | Orca Agent | Customers can rely on mcp client connectors as part of a governed Orca execution runtime. | Define the production contract for MCP Client Connectors; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | MCP auth; tool registry | orca.mcp_client | orca.mcp_client.usage | orca.mcp_client_connected | mcp.server_ref | MCP Client Connectors is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | MCP client tests pass with fake server. | Pending implementation. | Gemini CLI, MCP, and enterprise coding agents are expanding through tool ecosystems. | Orca can be a safe CLI/MCP runtime for approved tools and integrations. | Fake adapters are required; no real credentials in default tests.
ELK-ORCA-PROD-063 | Orca | GitHub Integration | Proposed | P0 | 5 - MCP Tools Integrations | Week 7-8 | Orca Agent | Customers can rely on github integration as part of a governed Orca execution runtime. | Define the production contract for GitHub Integration; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Integrations base; action policy | orca.integrations.github | orca.integrations.github.usage | orca.github_action_requested; orca.github_result_received | github.ref | GitHub Integration is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | GitHub integration tests pass with fake adapter. | Pending implementation. | Gemini CLI, MCP, and enterprise coding agents are expanding through tool ecosystems. | Orca can be a safe CLI/MCP runtime for approved tools and integrations. | Fake adapters are required; no real credentials in default tests.
ELK-ORCA-PROD-064 | Orca | Jira Notion Slack Integrations | Proposed | P1 | 5 - MCP Tools Integrations | Week 7-8 | Orca Agent | Customers can rely on jira notion slack integrations as part of a governed Orca execution runtime. | Define the production contract for Jira Notion Slack Integrations; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Existing integrations | orca.integrations | orca.integrations.usage | orca.integration_action_requested | integration.ref | Jira Notion Slack Integrations is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Fake integration tests pass. | Pending implementation. | Gemini CLI, MCP, and enterprise coding agents are expanding through tool ecosystems. | Orca can be a safe CLI/MCP runtime for approved tools and integrations. | Fake adapters are required; no real credentials in default tests.
ELK-ORCA-PROD-065 | Orca | Webhook Delivery | Proposed | P1 | 5 - MCP Tools Integrations | Week 7-8 | Orca Agent | Customers can rely on webhook delivery as part of a governed Orca execution runtime. | Define the production contract for Webhook Delivery; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Webhook modules | orca.webhooks | orca.webhooks.usage | orca.webhook_delivered; orca.webhook_failed | webhook.delivery | Webhook Delivery is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Webhook tests pass. | Pending implementation. | Gemini CLI, MCP, and enterprise coding agents are expanding through tool ecosystems. | Orca can be a safe CLI/MCP runtime for approved tools and integrations. | Fake adapters are required; no real credentials in default tests.
ELK-ORCA-PROD-066 | Orca | SDK Contracts | Proposed | P1 | 5 - MCP Tools Integrations | Week 7-8 | Orca Agent | Customers can rely on sdk contracts as part of a governed Orca execution runtime. | Define the production contract for SDK Contracts; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | packages/sdk-js; packages/sdk-py | orca.sdk | orca.sdk.usage | orca.sdk_updated | sdk.contract | SDK Contracts is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | SDK tests pass. | Pending implementation. | Gemini CLI, MCP, and enterprise coding agents are expanding through tool ecosystems. | Orca can be a safe CLI/MCP runtime for approved tools and integrations. | Fake adapters are required; no real credentials in default tests.
ELK-ORCA-PROD-067 | Orca | Plugin Marketplace Policy | Proposed | P1 | 5 - MCP Tools Integrations | Week 7-8 | Security Agent | Customers can rely on plugin marketplace policy as part of a governed Orca execution runtime. | Define the production contract for Plugin Marketplace Policy; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Plugin modules | orca.plugins | orca.plugins.usage | orca.plugin_validated; orca.plugin_rejected | plugin.validation_report | Plugin Marketplace Policy is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Plugin policy tests pass. | Pending implementation. | Gemini CLI, MCP, and enterprise coding agents are expanding through tool ecosystems. | Orca can be a safe CLI/MCP runtime for approved tools and integrations. | Fake adapters are required; no real credentials in default tests.
ELK-ORCA-PROD-068 | Orca | Connector Test Harness | Proposed | P0 | 5 - MCP Tools Integrations | Week 7-8 | QA Agent | Customers can rely on connector test harness as part of a governed Orca execution runtime. | Define the production contract for Connector Test Harness; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Integrations; MCP client | orca.integration_tests | orca.integration_tests.usage | orca.integration_tests_completed | integration.test_report | Connector Test Harness is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Integration test suite passes. | Pending implementation. | Gemini CLI, MCP, and enterprise coding agents are expanding through tool ecosystems. | Orca can be a safe CLI/MCP runtime for approved tools and integrations. | Fake adapters are required; no real credentials in default tests.
ELK-ORCA-PROD-069 | Orca | Repository Intake | Proposed | P0 | 6 - Coding Product Workflows | Week 9-10 | Orca Agent | Customers can rely on repository intake as part of a governed Orca execution runtime. | Define the production contract for Repository Intake; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Sandbox; session model | orca.repo | orca.repo.usage | orca.repo_intake_completed | repo.intake_report | Repository Intake is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Repo intake tests pass. | Pending implementation. | Codex, Copilot, Devin, Cursor, and Sourcegraph converge around repo context, patches, tests, and PR-ready reports. | Orca delivers code/product work with evidence and approvals. | Patch/test/report workflows must respect sandbox and handoff boundaries.
ELK-ORCA-PROD-070 | Orca | Context Index | Proposed | P0 | 6 - Coding Product Workflows | Week 9-10 | Orca Agent | Customers can rely on context index as part of a governed Orca execution runtime. | Define the production contract for Context Index; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Repo intake; secrets guard | orca.context | orca.context.usage | orca.context_indexed | context.index | Context Index is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Context tests pass. | Pending implementation. | Codex, Copilot, Devin, Cursor, and Sourcegraph converge around repo context, patches, tests, and PR-ready reports. | Orca delivers code/product work with evidence and approvals. | Patch/test/report workflows must respect sandbox and handoff boundaries.
ELK-ORCA-PROD-071 | Orca | Plan Patch Test Report Workflow | Proposed | P0 | 6 - Coding Product Workflows | Week 9-10 | Orca Agent | Customers can rely on plan patch test report workflow as part of a governed Orca execution runtime. | Define the production contract for Plan Patch Test Report Workflow; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Plan, sandbox, approvals | orca.workflow.coding | orca.workflow.coding.usage | orca.run_completed | orca.report; orca.patch | Plan Patch Test Report Workflow is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Workflow tests pass. | Pending implementation. | Codex, Copilot, Devin, Cursor, and Sourcegraph converge around repo context, patches, tests, and PR-ready reports. | Orca delivers code/product work with evidence and approvals. | Patch/test/report workflows must respect sandbox and handoff boundaries.
ELK-ORCA-PROD-072 | Orca | Patch Artifact Builder | Proposed | P0 | 6 - Coding Product Workflows | Week 9-10 | Orca Agent | Customers can rely on patch artifact builder as part of a governed Orca execution runtime. | Define the production contract for Patch Artifact Builder; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Patch sandbox | orca.patch | orca.patch.usage | orca.patch_created | orca.patch | Patch Artifact Builder is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Patch builder tests pass. | Pending implementation. | Codex, Copilot, Devin, Cursor, and Sourcegraph converge around repo context, patches, tests, and PR-ready reports. | Orca delivers code/product work with evidence and approvals. | Patch/test/report workflows must respect sandbox and handoff boundaries.
ELK-ORCA-PROD-073 | Orca | Test Runner | Proposed | P0 | 6 - Coding Product Workflows | Week 9-10 | Orca Agent | Customers can rely on test runner as part of a governed Orca execution runtime. | Define the production contract for Test Runner; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Shell command policy; repo intake | orca.tests | orca.tests.usage | orca.test_run_completed | orca.test_result | Test Runner is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Test runner tests pass. | Pending implementation. | Codex, Copilot, Devin, Cursor, and Sourcegraph converge around repo context, patches, tests, and PR-ready reports. | Orca delivers code/product work with evidence and approvals. | Patch/test/report workflows must respect sandbox and handoff boundaries.
ELK-ORCA-PROD-074 | Orca | PR Summary Builder | Proposed | P1 | 6 - Coding Product Workflows | Week 9-10 | Orca Agent | Customers can rely on pr summary builder as part of a governed Orca execution runtime. | Define the production contract for PR Summary Builder; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Patch artifact; GitHub integration | orca.pr | orca.pr.usage | orca.pr_summary_created | pr.summary | PR Summary Builder is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | PR summary tests pass. | Pending implementation. | Codex, Copilot, Devin, Cursor, and Sourcegraph converge around repo context, patches, tests, and PR-ready reports. | Orca delivers code/product work with evidence and approvals. | Patch/test/report workflows must respect sandbox and handoff boundaries.
ELK-ORCA-PROD-075 | Orca | Code Review Workflow | Proposed | P0 | 6 - Coding Product Workflows | Week 9-10 | Orca Agent | Customers can rely on code review workflow as part of a governed Orca execution runtime. | Define the production contract for Code Review Workflow; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Context index; eval/report | orca.code_review | orca.code_review.usage | orca.code_review_completed | orca.review_report | Code Review Workflow is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Code review tests pass. | Pending implementation. | Codex, Copilot, Devin, Cursor, and Sourcegraph converge around repo context, patches, tests, and PR-ready reports. | Orca delivers code/product work with evidence and approvals. | Patch/test/report workflows must respect sandbox and handoff boundaries.
ELK-ORCA-PROD-076 | Orca | Security Review Workflow | Proposed | P0 | 6 - Coding Product Workflows | Week 9-10 | Security Agent | Customers can rely on security review workflow as part of a governed Orca execution runtime. | Define the production contract for Security Review Workflow; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Code review; secret guard | orca.security_review | orca.security_review.usage | orca.security_review_completed | security.review_report | Security Review Workflow is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Security review tests pass. | Pending implementation. | Codex, Copilot, Devin, Cursor, and Sourcegraph converge around repo context, patches, tests, and PR-ready reports. | Orca delivers code/product work with evidence and approvals. | Patch/test/report workflows must respect sandbox and handoff boundaries.
ELK-ORCA-PROD-077 | Orca | Docs Generation Workflow | Proposed | P1 | 6 - Coding Product Workflows | Week 9-10 | Orca Agent | Customers can rely on docs generation workflow as part of a governed Orca execution runtime. | Define the production contract for Docs Generation Workflow; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Patch artifact; reports | orca.docs | orca.docs.usage | orca.docs_generated | docs.report | Docs Generation Workflow is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Docs workflow tests pass. | Pending implementation. | Codex, Copilot, Devin, Cursor, and Sourcegraph converge around repo context, patches, tests, and PR-ready reports. | Orca delivers code/product work with evidence and approvals. | Patch/test/report workflows must respect sandbox and handoff boundaries.
ELK-ORCA-PROD-078 | Orca | Product Builder Workflow | Proposed | P1 | 6 - Coding Product Workflows | Week 9-10 | Product Agent | Customers can rely on product builder workflow as part of a governed Orca execution runtime. | Define the production contract for Product Builder Workflow; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Coding workflow; Studio/Omni handoffs | orca.product_builder | orca.product_builder.usage | orca.product_workflow_completed | product.build_report | Product Builder Workflow is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Manual product workflow smoke. | Pending implementation. | Codex, Copilot, Devin, Cursor, and Sourcegraph converge around repo context, patches, tests, and PR-ready reports. | Orca delivers code/product work with evidence and approvals. | Patch/test/report workflows must respect sandbox and handoff boundaries.
ELK-ORCA-PROD-079 | Orca | Studio Handoff | Proposed | P0 | 6 - Coding Product Workflows | Week 9-10 | Studio Agent; Orca Agent | Customers can rely on studio handoff as part of a governed Orca execution runtime. | Define the production contract for Studio Handoff; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Studio roadmap | orca.handoff.studio | orca.handoff.studio.usage | orca.studio_handoff_received; orca.result_returned | studio.handoff_ref | Studio Handoff is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Synthetic handoff test passes. | Pending implementation. | Codex, Copilot, Devin, Cursor, and Sourcegraph converge around repo context, patches, tests, and PR-ready reports. | Orca delivers code/product work with evidence and approvals. | Patch/test/report workflows must respect sandbox and handoff boundaries.
ELK-ORCA-PROD-080 | Orca | Omni Handoff | Proposed | P0 | 6 - Coding Product Workflows | Week 9-10 | Omni Agent; Orca Agent | Customers can rely on omni handoff as part of a governed Orca execution runtime. | Define the production contract for Omni Handoff; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Omni roadmap | orca.handoff.omni | orca.handoff.omni.usage | orca.omni_handoff_received; orca.result_returned | omni.handoff_ref | Omni Handoff is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Synthetic Omni handoff test passes. | Pending implementation. | Codex, Copilot, Devin, Cursor, and Sourcegraph converge around repo context, patches, tests, and PR-ready reports. | Orca delivers code/product work with evidence and approvals. | Patch/test/report workflows must respect sandbox and handoff boundaries.
ELK-ORCA-PROD-081 | Orca | Trace IDs | Proposed | P0 | 7 - Observability Eval Audit | Week 11-12 | Orca Agent | Customers can rely on trace ids as part of a governed Orca execution runtime. | Define the production contract for Trace IDs; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Logging; run model | orca.tracing | orca.tracing.usage | orca.trace_created | trace.record | Trace IDs is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Trace tests pass. | Pending implementation. | Enterprise coding agents need traces, metrics, reports, evals, and audit to be trusted. | Orca competes through evidence and measured execution quality. | Raw code, secrets, and private prompts are redacted from default telemetry.
ELK-ORCA-PROD-082 | Orca | Tamper Evident Audit | Proposed | P0 | 7 - Observability Eval Audit | Week 11-12 | Security Agent | Customers can rely on tamper evident audit as part of a governed Orca execution runtime. | Define the production contract for Tamper Evident Audit; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Audit modules | orca.audit | orca.audit.usage | orca.audit_recorded | audit.log | Tamper Evident Audit is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Audit verify tests pass. | Pending implementation. | Enterprise coding agents need traces, metrics, reports, evals, and audit to be trusted. | Orca competes through evidence and measured execution quality. | Raw code, secrets, and private prompts are redacted from default telemetry.
ELK-ORCA-PROD-083 | Orca | Read Only Events Feed | Proposed | P0 | 7 - Observability Eval Audit | Week 11-12 | Orca Agent | Customers can rely on read only events feed as part of a governed Orca execution runtime. | Define the production contract for Read Only Events Feed; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Event contracts | orca.events | orca.events.usage | orca.events_listed | event.page | Read Only Events Feed is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Event feed tests pass. | Pending implementation. | Enterprise coding agents need traces, metrics, reports, evals, and audit to be trusted. | Orca competes through evidence and measured execution quality. | Raw code, secrets, and private prompts are redacted from default telemetry.
ELK-ORCA-PROD-084 | Orca | Metrics Dashboard API | Proposed | P1 | 7 - Observability Eval Audit | Week 11-12 | Orca Agent | Customers can rely on metrics dashboard api as part of a governed Orca execution runtime. | Define the production contract for Metrics Dashboard API; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Usage meters; traces | orca.metrics | orca.metrics.usage | orca.metric_recorded | metric.record | Metrics Dashboard API is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Metrics tests pass. | Pending implementation. | Enterprise coding agents need traces, metrics, reports, evals, and audit to be trusted. | Orca competes through evidence and measured execution quality. | Raw code, secrets, and private prompts are redacted from default telemetry.
ELK-ORCA-PROD-085 | Orca | Evaluation Suites | Proposed | P0 | 7 - Observability Eval Audit | Week 11-12 | QA Agent | Customers can rely on evaluation suites as part of a governed Orca execution runtime. | Define the production contract for Evaluation Suites; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Coding workflows; policy tests | orca.evals | orca.evals.usage | orca.eval_completed | eval.report | Evaluation Suites is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Eval suite passes in fake/local mode. | Pending implementation. | Enterprise coding agents need traces, metrics, reports, evals, and audit to be trusted. | Orca competes through evidence and measured execution quality. | Raw code, secrets, and private prompts are redacted from default telemetry.
ELK-ORCA-PROD-086 | Orca | Agent Leaderboard | Proposed | P1 | 7 - Observability Eval Audit | Week 11-12 | Orca Agent | Customers can rely on agent leaderboard as part of a governed Orca execution runtime. | Define the production contract for Agent Leaderboard; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Metrics; agent registry | orca.agents | orca.agents.usage | orca.agent_score_updated | agent.scorecard | Agent Leaderboard is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Leaderboard tests pass. | Pending implementation. | Enterprise coding agents need traces, metrics, reports, evals, and audit to be trusted. | Orca competes through evidence and measured execution quality. | Raw code, secrets, and private prompts are redacted from default telemetry.
ELK-ORCA-PROD-087 | Orca | Report Builder | Proposed | P0 | 7 - Observability Eval Audit | Week 11-12 | Orca Agent | Customers can rely on report builder as part of a governed Orca execution runtime. | Define the production contract for Report Builder; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Artifacts; traces | orca.reports | orca.reports.usage | orca.report_created | orca.report | Report Builder is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Report tests pass. | Pending implementation. | Enterprise coding agents need traces, metrics, reports, evals, and audit to be trusted. | Orca competes through evidence and measured execution quality. | Raw code, secrets, and private prompts are redacted from default telemetry.
ELK-ORCA-PROD-088 | Orca | Log Export | Proposed | P1 | 7 - Observability Eval Audit | Week 11-12 | Orca Agent | Customers can rely on log export as part of a governed Orca execution runtime. | Define the production contract for Log Export; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Logging; audit | orca.logs | orca.logs.usage | orca.log_exported | log.export | Log Export is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Log export tests pass. | Pending implementation. | Enterprise coding agents need traces, metrics, reports, evals, and audit to be trusted. | Orca competes through evidence and measured execution quality. | Raw code, secrets, and private prompts are redacted from default telemetry.
ELK-ORCA-PROD-089 | Orca | Incident Postmortem | Proposed | P0 | 7 - Observability Eval Audit | Week 11-12 | Security Agent | Customers can rely on incident postmortem as part of a governed Orca execution runtime. | Define the production contract for Incident Postmortem; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Reports; incidents | orca.incidents | orca.incidents.usage | orca.postmortem_created | postmortem.report | Incident Postmortem is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Postmortem tests pass. | Pending implementation. | Enterprise coding agents need traces, metrics, reports, evals, and audit to be trusted. | Orca competes through evidence and measured execution quality. | Raw code, secrets, and private prompts are redacted from default telemetry.
ELK-ORCA-PROD-090 | Orca | Performance Load Tests | Proposed | P1 | 7 - Observability Eval Audit | Week 11-12 | QA Agent | Customers can rely on performance load tests as part of a governed Orca execution runtime. | Define the production contract for Performance Load Tests; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Load test scripts | orca.performance | orca.performance.usage | orca.benchmark_completed | benchmark.report | Performance Load Tests is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | npm run test:load smoke passes. | Pending implementation. | Enterprise coding agents need traces, metrics, reports, evals, and audit to be trusted. | Orca competes through evidence and measured execution quality. | Raw code, secrets, and private prompts are redacted from default telemetry.
ELK-ORCA-PROD-091 | Orca | RBAC Admin Controls | Proposed | P0 | 8 - Enterprise Governance Release | Week 12-15 | Security Agent | Customers can rely on rbac admin controls as part of a governed Orca execution runtime. | Define the production contract for RBAC Admin Controls; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Auth/RBAC modules | orca.rbac | orca.rbac.usage | orca.rbac_denied; orca.rbac_allowed | rbac.policy | RBAC Admin Controls is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | RBAC tests pass. | Pending implementation. | Agent adoption in enterprises depends on governance, identity, quotas, docs, and launch evidence. | Orca becomes client-ready through controls, not autonomy claims. | Release blocks on approval bypass, sandbox, secret, MCP, or data-loss findings.
ELK-ORCA-PROD-092 | Orca | Quotas Rate Limits | Proposed | P0 | 8 - Enterprise Governance Release | Week 12-15 | Orca Agent | Customers can rely on quotas rate limits as part of a governed Orca execution runtime. | Define the production contract for Quotas Rate Limits; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Billing/quotas modules | orca.quotas | orca.quotas.usage | orca.quota_exceeded | quota.record | Quotas Rate Limits is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Quota tests pass. | Pending implementation. | Agent adoption in enterprises depends on governance, identity, quotas, docs, and launch evidence. | Orca becomes client-ready through controls, not autonomy claims. | Release blocks on approval bypass, sandbox, secret, MCP, or data-loss findings.
ELK-ORCA-PROD-093 | Orca | Provider Privacy Policy | Proposed | P0 | 8 - Enterprise Governance Release | Week 12-15 | Security Agent | Customers can rely on provider privacy policy as part of a governed Orca execution runtime. | Define the production contract for Provider Privacy Policy; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Model routing; secrets guard | orca.providers | orca.providers.usage | orca.provider_policy_updated | provider.policy | Provider Privacy Policy is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Provider policy tests pass. | Pending implementation. | Agent adoption in enterprises depends on governance, identity, quotas, docs, and launch evidence. | Orca becomes client-ready through controls, not autonomy claims. | Release blocks on approval bypass, sandbox, secret, MCP, or data-loss findings.
ELK-ORCA-PROD-094 | Orca | Compliance Readiness Report | Proposed | P1 | 8 - Enterprise Governance Release | Week 12-15 | Security Agent | Customers can rely on compliance readiness report as part of a governed Orca execution runtime. | Define the production contract for Compliance Readiness Report; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | NIST AI RMF; security controls | orca.compliance | orca.compliance.usage | orca.compliance_report_created | compliance.report | Compliance Readiness Report is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Report review passes. | Pending implementation. | Agent adoption in enterprises depends on governance, identity, quotas, docs, and launch evidence. | Orca becomes client-ready through controls, not autonomy claims. | Release blocks on approval bypass, sandbox, secret, MCP, or data-loss findings.
ELK-ORCA-PROD-095 | Orca | Production Documentation | Proposed | P0 | 8 - Enterprise Governance Release | Week 12-15 | Documentation Agent | Customers can rely on production documentation as part of a governed Orca execution runtime. | Define the production contract for Production Documentation; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Implemented features | orca.docs | orca.docs.usage | orca.docs_updated | docs.orca | Production Documentation is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Documentation review passes. | Pending implementation. | Agent adoption in enterprises depends on governance, identity, quotas, docs, and launch evidence. | Orca becomes client-ready through controls, not autonomy claims. | Release blocks on approval bypass, sandbox, secret, MCP, or data-loss findings.
ELK-ORCA-PROD-096 | Orca | Package Release Gate | Proposed | P0 | 8 - Enterprise Governance Release | Week 12-15 | Release Agent | Customers can rely on package release gate as part of a governed Orca execution runtime. | Define the production contract for Package Release Gate; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | App scripts; docs | orca.release | orca.release.usage | orca.release_checked | release.report | Package Release Gate is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | cd elkhedr-orca && npm run manifest && npm test | Pending implementation. | Agent adoption in enterprises depends on governance, identity, quotas, docs, and launch evidence. | Orca becomes client-ready through controls, not autonomy claims. | Release blocks on approval bypass, sandbox, secret, MCP, or data-loss findings.
ELK-ORCA-PROD-097 | Orca | Beta Pilot Pack | Proposed | P0 | 8 - Enterprise Governance Release | Week 12-15 | Product Agent | Customers can rely on beta pilot pack as part of a governed Orca execution runtime. | Define the production contract for Beta Pilot Pack; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Docs; eval suites | orca.beta | orca.beta.usage | orca.beta_started | beta.pack | Beta Pilot Pack is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Beta dry run passes with synthetic data. | Pending implementation. | Agent adoption in enterprises depends on governance, identity, quotas, docs, and launch evidence. | Orca becomes client-ready through controls, not autonomy claims. | Release blocks on approval bypass, sandbox, secret, MCP, or data-loss findings.
ELK-ORCA-PROD-098 | Orca | Launch Checklist | Proposed | P0 | 8 - Enterprise Governance Release | Week 12-15 | Coordinator Agent | Customers can rely on launch checklist as part of a governed Orca execution runtime. | Define the production contract for Launch Checklist; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | All P0 tasks | orca.launch | orca.launch.usage | orca.launch_checked | launch.memo | Launch Checklist is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Go/no-go memo has evidence for each P0 requirement. | Pending implementation. | Agent adoption in enterprises depends on governance, identity, quotas, docs, and launch evidence. | Orca becomes client-ready through controls, not autonomy claims. | Release blocks on approval bypass, sandbox, secret, MCP, or data-loss findings.
ELK-ORCA-PROD-099 | Orca | Post Launch KPIs | Proposed | P1 | 8 - Enterprise Governance Release | Week 12-15 | Product Agent | Customers can rely on post launch kpis as part of a governed Orca execution runtime. | Define the production contract for Post Launch KPIs; implement or verify the runtime path; add synthetic fixtures and negative tests; document operator behavior; update this CSV row with evidence after verification. | Metrics; usage meters | orca.analytics | orca.analytics.usage | orca.kpi_report_created | kpi.report | Post Launch KPIs is implemented, documented, tested, emits the expected events/artifacts, and cannot bypass approval, sandbox, audit, or standalone boundary rules. | Generate first synthetic KPI report. | Pending implementation. | Agent adoption in enterprises depends on governance, identity, quotas, docs, and launch evidence. | Orca becomes client-ready through controls, not autonomy claims. | Release blocks on approval bypass, sandbox, secret, MCP, or data-loss findings.